

**Software Engineering 2: “PowerEnJoy”**

**Project Plan (V. 1.0)**

Authors:

Sergio CAPRARA

Soheil GHANBARI

Erica TINTI

Milan, Italy

15/01/2017

**Table of contents**

[1. Introduction 3](#_Toc472332391)

[1.1 Revision History 3](#_Toc472332392)

[1.2 Purpose and Scope 3](#_Toc472332393)

[1.3 Definitions and Abbreviations 3](#_Toc472332394)

[1.4 Reference Documents 4](#_Toc472332395)

[2. Project size, cost and effort estimation 5](#_Toc472332396)

[2.1 Size estimation: function points 5](#_Toc472332397)

[2.2 Cost and effort estimation: COCOMO II 6](#_Toc472332398)

[3. Schedule 8](#_Toc472332399)

[4. Resource allocation 9](#_Toc472332400)

[5. Risk management 10](#_Toc472332401)

[6. Hours of work 11](#_Toc472332402)

# Introduction

## Revision History

|  |  |  |  |
| --- | --- | --- | --- |
| **Version** | **Date** | **Authors** | **Description** |
| 1.0 | 22/01/2017 | S. Caprara, S. Ghanbari, E. Tinti | First release |

## Purpose and Scope

In this document, we are providing details on how the components described in the Design Document will be integrated. To ensure that the interaction between them will give the expected results, we are choosing the method to follow and we are keeping in mind that the Integration Test of a component will be done after having Unit Tested it.

In the following chapters, you will find detailed descriptions of the tests and the name of the tools to be used.

## Definitions and Abbreviations

* **User:** the person registered to the system and allowed to access to its functions.
* **Operator:** a person with technical skills, that fixes car issues.
* **App:** short term used to define a mobile application.
* **Power Plug:** a column with one or more electricity socket where it is possible to charge the car.
* **Safe Area** (or Parking Area): a parking area with parking shared with all the other divers and not especially reserved to PowerEnjoy.
* **Special Parking Area** (or Power Station): a parking area reserved exclusively to PowerEnjoy cars where, for each parking space there is a Power Plug where it is possible to charge a car.
* **Car:** PowerEnjoy car.
* **Reservation:** the relation between a user and a car, that allows the user to start using the car. The reservation guarantees that no one else can reserve and use the reserved car till the end of the rental.
* **DB:** database, the collection of system data.
* **DAO:** Data Access Object.
* **Pojo:** Plain Old Java Object. Object having only getter and setter methods.

## Reference Documents

The documents used as a reference to provide the design document are:

* Assignments AA 2016-2017.pdf
* Project planning example document.pdf
* RASD\_PowerEnjoy\_Caprara\_Ghanbari\_Tinti
* DesignDocument\_PowerEnjoy\_Caprara\_Ghanbari\_Tinti
* TestPlan\_PowerEnjoy\_Caprara\_Ghanbari\_Tinti\_v1.0.pdf

# Project size, cost and effort estimation

## Size estimation: function points

Only when the Integration Test Plan document will be complete, it will be possible to start with the integration testing phase.

## Cost and effort estimation: COCOMO II

Our system has many components, organised in two levels of granularity.

The higher level of components of our system that need to be integrated are:

* User Application
* Operator Application
* Controller
* Model
* Database

The listed components are divided into lower level components, that will need integration testing.

# Schedule

The following paragraphs contain the detail of the Test Cases defined in the previous chapter.

# Resource allocation

For supporting and automating Integration Tests we will use two testing tools: JUnit and Arquillian.

# Risk management

Integration tests should also verify the responses of the system in specific cases, such as

# Hours of work

To make this document we have spent:

* Sergio Caprara, 14 hours
* Soheil Ghanbari, 8 hours
* Erica Tinti, 14 hours