

**Software Engineering 2: “PowerEnJoy”**

**Project Plan (V. 1.0)**

Authors:

Sergio CAPRARA

Soheil GHANBARI

Erica TINTI

Milan, Italy

15/01/2017

**Table of contents**

[1. Introduction 3](#_Toc472332391)

[1.1 Revision History 3](#_Toc472332392)

[1.2 Purpose and Scope 3](#_Toc472332393)

[1.3 Definitions and Abbreviations 3](#_Toc472332394)

[1.4 Reference Documents 4](#_Toc472332395)

[2. Project size, cost and effort estimation 5](#_Toc472332396)

[2.1 Size estimation: function points 5](#_Toc472332397)

[2.2 Cost and effort estimation: COCOMO II 6](#_Toc472332398)

[3. Schedule 8](#_Toc472332399)

[4. Resource allocation 9](#_Toc472332400)

[5. Risk management 10](#_Toc472332401)

[6. Hours of work 11](#_Toc472332402)

# Introduction

## Revision History

|  |  |  |  |
| --- | --- | --- | --- |
| **Version** | **Date** | **Authors** | **Description** |
| 1.0 | 22/01/2017 | S. Caprara, S. Ghanbari, E. Tinti | First release |

## Purpose and Scope

In this document, we are providing details on how the components described in the Design Document will be integrated. To ensure that the interaction between them will give the expected results, we are choosing the method to follow and we are keeping in mind that the Integration Test of a component will be done after having Unit Tested it.

In the following chapters, you will find detailed descriptions of the tests and the name of the tools to be used.

## Definitions and Abbreviations

* **User:** the person registered to the system and allowed to access to its functions.
* **Operator:** a person with technical skills, that fixes car issues.
* **App:** short term used to define a mobile application.
* **Power Plug:** a column with one or more electricity socket where it is possible to charge the car.
* **Safe Area** (or Parking Area): a parking area with parking shared with all the other divers and not especially reserved to PowerEnjoy.
* **Special Parking Area** (or Power Station): a parking area reserved exclusively to PowerEnjoy cars where, for each parking space there is a Power Plug where it is possible to charge a car.
* **Car:** PowerEnjoy car.
* **Reservation:** the relation between a user and a car, that allows the user to start using the car. The reservation guarantees that no one else can reserve and use the reserved car till the end of the rental.
* **DB:** database, the collection of system data.
* **DAO:** Data Access Object.
* **Pojo:** Plain Old Java Object. Object having only getter and setter methods.

## Reference Documents

The documents used as a reference to provide the design document are:

* Assignments AA 2016-2017.pdf
* Project planning example document.pdf
* RASD\_PowerEnjoy\_Caprara\_Ghanbari\_Tinti
* DesignDocument\_PowerEnjoy\_Caprara\_Ghanbari\_Tinti
* TestPlan\_PowerEnjoy\_Caprara\_Ghanbari\_Tinti\_v1.0.pdf

# Project size, cost, and effort estimation

This section of the document provides

## Size estimation: function points

The size of the project we are working on, will be estimated using the Function Point Analysis approach. This technique is based on five major components:

* External Input, all operation that takes data in from the external environment
* External Output, all operation that sends data out
* External Inquiry, all operation involving both input and output
* Internal Logic Files, data used and managed by our application
* External Interface Files, data used by our system but generated by other applications

The tables used for the estimation are provided here.

|  |  |  |  |
| --- | --- | --- | --- |
| **File Type Referenced** | **Data elements** | | |
| **1-4** | **5-15** | **> 15** |
| **0-1** | Low | Low | Avg |
| **2** | Low | Avg | High |
| **3 or more** | Avg | High | High |

**Table 1: External Input**

|  |  |  |  |
| --- | --- | --- | --- |
| **File Type Referenced** | **Data elements** | | |
| **1-5** | **6-19** | **> 19** |
| **0-1** | Low | Low | Avg |
| **2-3** | Low | Avg | High |
| **4 or more** | Avg | High | High |

**Table 2: External Output and External Inquiries**

|  |  |  |  |
| --- | --- | --- | --- |
| **Record Element Type** | **Data Elements** | | |
| **1-19** | **20-50** | **> 50** |
| **1** | Low | Low | Avg |
| **2-5** | Low | Avg | High |
| **6 or more** | Avg | High | High |

**Table 3: Internal Logic Files and External Interface Files**

|  |  |  |  |
| --- | --- | --- | --- |
| **Type of Component** | **Complexity of Components** | | |
| **Low** | **Average** | **High** |
| **External Inputs** | 3 | 4 | 6 |
| **External Outputs** | 4 | 5 | 7 |
| **External Inquiries** | 3 | 4 | 6 |
| **Internal Logic Files** | 7 | 10 | 15 |
| **External Logic Files** | 5 | 7 | 10 |

**Table 4: Unadjusted Function Points**

## External Inputs

**Common functions**

The Login and Logout (for both users and operators) are low complexity functions, because they involve just one file containing the information, so they get 3 FPs each.

**User functions**

User Registration is a function that can be classified as having an average complexity, because it deals with different data and because more than one file is referenced. This leads to 4 FPs.

The Profile Update function involves many fields that need to be updated on the DB, so it has a medium complexity.

The Payment Method Update operation requires the system to check if the new credit card is valid. For this reasons the operation has a medium complexity, corresponding to 4 FPs.

The Cancel Reservation operation has a low complexity because it references two type of files but has few data. So, it has 3 FPs.

**Operator functions**

The Maintenance Request is a simple operation, involving only one component. For this reason, it has low complexity and gets 3 FPs.

The End of Maintenance operation involves few components and has a low complexity, leading to 3 FPs.

|  |  |  |
| --- | --- | --- |
| **EI** | **Complexity** | **FPs** |
| Login  Logout  User Registration  Profile Update  Payment Method Update  Cancel Reservation  Maintenance Request  End of Maintenance | Low  Low  Average  Average  Average  Low  Low  Low | 3  3  4  4  4  3  3  3 |
| **Total** | | **27** |

## External Outputs

The operation for Registration Confirmation has a low complexity, that corresponds to 4 FPs.

The Reservation Expiration operation involves some components and has a medium complexity. Because of this, it has 5 FPs.

The Money Charge Information is an operation sent by the system to the user and requires the interaction with many different components and has many interactions. For this reason, the complexity is high and the assigned FPs are 7.

Position Feedback medium 5 FPs

|  |  |  |
| --- | --- | --- |
| **EO** | **Complexity** | **FPs** |
| Registration Confirmation  Reservation Expiration  Money Charge Information  Position Feedback | Low  Average  High  Average | 4  5  7  5 |
| **Total** | | **21** |

## External Inquiries

**User functions**

Car Lookup operation involves more than one component and contains many data, so its complexity is medium, corresponding to 4 FPs.

The Car Information is a simple operation to retrieve car details. It references just one component and contains few data. Because of this, the complexity is low and corresponds to 3 FPs.

The Reserve Car operation has a low complexity, so it gets 3 FPs.

Car Unlock operation has a medium complexity because it involves different components and requires many interactions. It corresponds to 4 FPs.

Parking Areas Request and Special Parking Areas Request are simple operations, involving only one component each. Their complexity is low, corresponding to 3 FPs each.

View Profile low 3 FPs

**Operator functions**

Car List Retrieve low 3 FPs

Car Details medium 4FPs

|  |  |  |
| --- | --- | --- |
| **EQ** | **Complexity** | **FPs** |
| Car Lookup  Car Information (user)  Reserve Car  Car Unlock  Parking Areas Request  Special Parking Areas Request  View Profile  Car List Retrieve  Car Details (operator) | Average  Low  Low  Average  Low  Low  Low  Low  Average | 4  3  3  4  3  3  3  3  4 |
| **Total** | | **30** |

## Internal Logic Files

Car Info medium 10 FPs

User medium 10 FPs

Parking Area low 7 FPs

Special Parking Area low 7 FPs

Operator low 7 FPs

|  |  |  |
| --- | --- | --- |
| **ILF** | **Complexity** | **FPs** |
| Car Info  User  Parking Area  Special Parking Area  Operator | Average  Average  Low  Low  Low | 10  10  7  7  7 |
| **Total** | | **41** |

## External Interface Files

The Licence Validation system is accessing an external source, by providing the information on the driving licence of the user and request the verification of this data. It can be considered as having a low complexity, so it corresponds to 5 FPs.

The system uses GPS Access for finding user and car locations or to find the coordinates of a specified address. All of these are low complexity tasks, corresponding to 5 FPs.

|  |  |  |
| --- | --- | --- |
| **EIF** | **Complexity** | **FPs** |
| Licence Validation  GPS Access  GPS Address Lookup | Low  Low  Low | 5  5  5 |
| **Total** | | **15** |

## Overall estimation

The results of the complexity estimation are provided in the following table.

|  |  |
| --- | --- |
| **Type of Component** | **FPs** |
| External Inputs  External Outputs  External Inquiries  Internal Logic Files  External Interface Files | 27  21  30  41  15 |
| **Total** | **134** |

Using this result, we can estimate the amount of total code lines in our applications.

## Cost and effort estimation: COCOMO II

The cost and effort estimation is made using the COCOMO II method.

## Scale Drivers

We provide here the table containing figures used in the evaluation. It is based on the following scale drivers:

* Precedentedness (PREC): the value depends on the experience the team has on projects similar to the current one.
* Development flexibility (FLEX): represents the possibility to make changes to the project based on the strictness of the external requirements.
* Risk resolution (RESL): consists in the capacity to solve problems and is strictly related to the risk analysis provided in this document.
* Team cohesion (TEAM): its value represents the capacity of the team members to work together and cooperate
* Process maturity (PMAT): states the level of maturity reached in the process.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Scale Factors** | **Very Low** | **Low** | **Nominal** | **High** | **Very High** | **Extra High** |
| **PREC** | thoroughly  unprecedented | largely  unprecedented | somewhat  unprecedented | generally  familiar | largely  familiar | thoroughly familiar |
| **SFj** | 6.20 | 4.96 | 3.72 | 2.48 | 1.24 | 0.00 |
| **FLEX** | rigorous | occasional  relaxation | some  relaxation | general  conformity | some  conformity | general goals |
| **SFj** | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0.00 |
| **RESL** | little (20%) | some (40%) | often (60%) | generally (75%) | mostly (90%) | full (100%) |
| **SFj** | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0.00 |
| **TEAM** | very difficult  interactions | some  difficult  interactions | basically  cooperative  interactions | largely  cooperative | highly  cooperative | seamless  interactions |
| **SFj** | 5.48 | 4.38 | 3.29 | 2.19 | 1.10 | 0.00 |
| **PMAT** | Level 1  Lower | Level 1  Upper | Level 2 | Level 3 | Level 4 | Level 5 |
| **SFj** | 7.80 | 6.24 | 4.68 | 3.12 | 1.56 | 0.00 |

The

## Cost Drivers

**Required Software Reliability**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **RELY Cost Drivers** | | | | | | |
| **RELY**  **Descriptors** | slightly  inconvenience  losses | easily recoverable  losses | moderate  recoverable | high financial  loss | risk to human life |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 0.82 | 0.92 | 1.00 | 1.10 | 1.26 | n/a |

**Data Base Size**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **DATA Cost Drivers** | | | | | | |
| **DATA**  **Descriptors** |  | D/P < 10 | 10 <= D/P <= 100 | 100 <= D/P <= 1000 | D/P > 1000 |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | n/a | 0.90 | 1.00 | 1.14 | 1.28 | n/a |

**Product Complexity**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **CPLX Cost Drivers** | | | | | | |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 0.73 | 0.87 | 1.00 | 1.17 | 1.34 | 1.74 |

**Developed for Reusability**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **RUSE Cost Drivers** | | | | | | |
| **RUSE**  **Descriptors** |  | None | Across project | Across program | Across product line | Across multiple product lines |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | n/a | 0.95 | 1.00 | 1.07 | 1.15 | 1.24 |

**Documentation Match to Life-Cycle Needs**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **DOCU Cost Drivers** | | | | | | |
| **DOCU**  **Descriptors** | Many life-cycle needs uncovered | Some life-cycle needs uncovered | Right-sized to life-cycle needs | Excessive for life-  cycle needs | Very excessive for life-cycle needs |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 0.81 | 0.91 | 1.00 | 1.11 | 1.23 | n/a |

**Execution Time Constraint**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **TIME Cost Drivers** | | | | | | |
| **TIME**  **Descriptors** |  |  | <= 50%  use of  available  execution  time | 70% use of  available  execution  time | 85% use of  available  execution  time | 95% use of  available  execution  time |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | n/a | n/a | 1.00 | 1.11 | 1.29 | 1.63 |

**Main Storage Constraint**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **STOR Cost Drivers** | | | | | | |
| **STOR**  **Descriptors** |  |  | <= 50%  use of  available  storage | 70% use of  available  storage | 85% use of  available  storage | 95% use of  available  storage |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | n/a | n/a | 1.00 | 1.05 | 1.17 | 1.46 |

**Platform Volatility**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **PVOL Cost Drivers** | | | | | | |
| **PVOL**  **Descriptors** |  | Major change every 12 mo, minor change every 1 mo | Major: 6mo; minor: 2wk | Major: 2mo, minor: 1wk | Major: 2wk; minor: 2 days |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | n/a | 0.87 | 1.00 | 1.15 | 1.30 | n/a |

**Analyst Capability**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **ACAP Cost Drivers** | | | | | | |
| **ACAP**  **Descriptors** | 15th percentile | 35th percentile | 55th percentile | 75th percentile | 90th percentile |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.42 | 1.19 | 1.00 | 0.85 | 0.71 | n/a |

**Programmer Capability**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **PCAP Cost Drivers** | | | | | | |
| **PCAP**  **Descriptors** | 15th percentile | 35th percentile | 55th percentile | 75th percentile | 90th percentile |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.34 | 1.15 | 1.00 | 0.88 | 0.76 | n/a |

**Personnel Continuity**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **PCON Cost Drivers** | | | | | | |
| **PCON**  **Descriptors** | 48% / year | 24% / year | 12% / year | 6% / year | 3% / year |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.29 | 1.12 | 1.00 | 0.90 | 0.81 | n/a |

**Applications Experience**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **APEX Cost Drivers** | | | | | | |
| **APEX**  **Descriptors** | <= 2  months | 6 months | 1 year | 3 years | 6 years |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.22 | 1.10 | 1.00 | 0.88 | 0.81 | n/a |

**Platform Experience**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **PLEX Cost Drivers** | | | | | | |
| **PLEX**  **Descriptors** | <= 2  months | 6 months | 1 year | 3 years | 6 years |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.19 | 1.09 | 1.00 | 0.91 | 0.85 | n/a |

**Language and Tool Experience**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **LTEX Cost Drivers** | | | | | | |
| **LTEX**  **Descriptors** | <= 2  months | 6 months | 1 year | 3 years | 6 years |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.20 | 1.09 | 1.00 | 0.91 | 0.84 | n/a |

**Use of Software Tools**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **TOOL Cost Drivers** | | | | | | |
| **TOOL**  **Descriptors** | edit, code, debug | simple, frontend,  backend CASE, little integration | Basic life-cycle tools, moderately integrated | strong, mature life-cycle tools,  moderately integrated | strong, mature, proactive life-cycle tools, well integrated with processes, methods, reuse |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.17 | 1.09 | 1.00 | 0.90 | 0.78 | n/a |

**Multisite Development**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **SITE Cost Drivers** | | | | | | |
| **SITE**  **Descriptors** | Intern-ational | Multi-city and multi-company | Multi-city or multi-company | Same city or metro area | Same building or complex | Fully collocated |
| **SITE Communications Descriptors** | Some phone, mail | Individual phone, fax | Narrow band email | Wideband electronic communi-  cation | Wideband  elect. comm., occasional video conf. | Interactive  multimedia |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.22 | 1.09 | 1.00 | 0.93 | 0.86 | 0.80 |

**Required Development Schedule**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **SCED Cost Drivers** | | | | | | |
| **SCED**  **Descriptors** | 75% of nominal | 85% of nominal | 100% of nominal | 130% of nominal | 160% of nominal |  |
| **Rating Level** | Very Low | Low | Nominal | High | Very High | Extra High |
| **Effort Multipliers** | 1.43 | 1.14 | 1.00 | 1.00 | 1.00 | n/a |

|  |  |  |
| --- | --- | --- |
| **Cost Driver** | **Factor** | **Value** |
| Required Software Reliability (RELY)  Data Base Size (DATA)  Product Complexity (CPLX)  Developed for Reusability (RUSE)  Documentation Match to Life-Cycle Needs (DOCU)  Execution Time Constraint (TIME)  Main Storage Constraint (STOR)  Platform Volatility (PVOL)  Analyst Capability (ACAP)  Programmer Capability (PCAP)  Personnel Continuity (PCON)  Applications Experience (APEX)  Platform Experience (PLEX)  Language and Tool Experience (LTEX)  Use of Software Tools (TOOL)  Multisite Development (SITE)  Required Development Schedule (SCED) | L | 5 |
| **Total** | | **15** |

# Schedule

The following paragraphs contain the detail of the Test Cases defined in the previous chapter.

# Resource allocation

For supporting and automating Integration Tests we will use two testing tools: JUnit and Arquillian.

# Risk management

Integration tests should also verify the responses of the system in specific cases, such as

# Hours of work

To make this document we have spent:

* Sergio Caprara, 14 hours
* Soheil Ghanbari, 8 hours
* Erica Tinti, 14 hours